## Stories
Story ID | Epic | Jira Key | Current Status | Merges In | BR Ref | Priority | Story Points (proposed) | Title | User Story | Acceptance Criteria (Given / When / Then) | Can Pull? | Builds Against (so no waiting) | Integrates With | Open Decisions | Notes
S01 | Authentication & Security | LMKT-11 | Done | LMKT-9, LMKT-10, LMKT-12, LMKT-56 | BR-01 | Must | 5 | Register for an account | As Joanna, a prospective self-directed investor, I want to register with my name, address, email and phone number so that I can start trading on my own without calling the dealing desk. | AC1. Given I am on the registration page, when I submit a valid name, address, email, phone number and a password that meets the password policy, then my account is created and I see a confirmation that I can now sign in. AC2. Given a required field is empty or badly formatted, when I submit, then no account is created and each problem field shows an inline message explaining how to fix it. AC3. Given an account already exists for my email address, when I submit, then registration is refused with a message that the email is already registered. AC4. Given my account has been created, when the stored record is inspected, then the password is held only as a salted hash. | Done | — | S02 | Q1 | Re-verify against delivered code.
S02 | Authentication & Security | LMKT-14 | Done | LMKT-13, LMKT-15, LMKT-57 | BR-01, §9.3 | Must | 3 | Sign in securely | As Joanna, a registered client, I want to sign in with my email and password so that I can get back to my positions and trade. | AC1. Given I have an active account, when I enter the correct email and password, then I am signed in and taken to my portfolio page. AC2. Given I enter a wrong password or an unregistered email, when I submit, then I am not signed in and see the same generic message in both cases. AC3. Given I am not signed in, when I open any client page or call any client API, then I am sent to sign-in (UI) or receive 401 (API). AC4. Given any sign-in attempt, then a security event is recorded with the account, the outcome and a UTC timestamp. AC5. Given any sign-in request, then credentials are only transmitted over HTTPS. | Done | — | All client stories |  | Re-verify AC4–5 against delivered code.
S03 | Authentication & Security | LMKT-18 | To Do |  | BR-03 | Should | 3 | Lock my account after repeated failed sign-ins | As Joanna, I want my account locked after repeated wrong passwords so that someone guessing my password cannot get in. | AC1. Given I have failed to sign in 2 times in a row, when a 3rd consecutive attempt fails, then my account is locked and I am told for how long. AC2. Given my account is locked, when I enter the correct password, then sign-in is still refused. AC3. Given fewer than 3 consecutive failures, when I sign in successfully, then the failure count resets to zero. AC4. Given my account is locked, when the lockout period has passed (configurable, default 15 minutes), then I can sign in again. AC5. Given an account becomes locked, then a security event is recorded. | Ready now | Seed data: locked test client (C3); config (C5) | S02 | Q3 (non-blocking) | If the PO wants manual unlock by staff instead, that becomes a separate story.
S04 | Authentication & Security | LMKT-17 | Done |  | BR-03 | Should | 2 | Sign me out automatically after inactivity | As Joanna, I want my session to end if I walk away from my screen so that nobody can use my account on an unattended computer. | AC1. Given I am signed in, when there is no activity for the inactivity timeout (configurable, default 1 minute per BRS), then my session ends and my next action takes me to sign-in with the message 'You were signed out due to inactivity'. AC2. Given I interact before the timeout, then the timer restarts. AC3. Given my session has expired, when the old session token is used against any API, then the API returns 401. AC4. Given I am part-way through entering an order, when the session times out, then no order is submitted on my behalf. | Done | Config (C5) | — | Q2 (non-blocking) | Re-verify the timeout is configurable.
S05 | Authentication & Security | NEW |  |  | BR-03 | Should | 1 | Sign out | As Joanna, I want to sign out when I'm finished so that my session cannot be reused by anyone else on this computer. | AC1. Given I am signed in, when I click Sign out, then my session is invalidated on the server and I am taken to the sign-in page. AC2. Given I have signed out, when the old session token is used against any API, then the API returns 401. AC3. Given I have signed out, when I press the browser Back button, then no account data is shown. | Ready now | Existing sign-in (S02 is Done) | —
S06 | Authentication & Security | NEW |  |  | BR-03 | Should | 2 | Cut off access for closed or expired accounts | As Risk & Compliance, I want closed, expired or deleted accounts to lose access immediately so that a compromised or terminated account cannot keep being used. | AC1. Given an account's status is closed, expired or deleted, when that client tries to sign in, then sign-in is refused with a message to contact the firm. AC2. Given that client still has an active session, when the session makes its next request, then the request is rejected with 401. AC3. Given access is cut off, then a security event is recorded with the account, the reason and a UTC timestamp. | Ready now | Seed data: closed and expired test clients (C3) | — |  | Order rejection for closed accounts lives in S08/S09, so this story does not wait on order placement.
S07 | Authentication & Security | LMKT-16 | Done |  | BR-02, §9.3 | Must | 3 | See and act on only my own account | As Joanna, I want my holdings, cash and orders to be visible and actionable only by me so that my financial information stays private. | AC1. Given I am signed in as client A, when I request holdings, cash, order history or an order's status, then only client A's data is returned. AC2. Given I am signed in as client A, when I request a resource belonging to client B by ID or URL, then I receive 403/404 with no client B data, and the attempt is recorded. AC3. Given any client request, then the client's identity is taken from the authenticated session, never from a request parameter. | Done | — | All client stories |  | Re-verify AC3 against delivered code; DoD item 5 keeps this true for every new endpoint.
S08 | Order Management | LMKT-55 | In Progress | LMKT-19, LMKT-31 | BR-04, §9.5 | Must | 5 | Place a market buy order | As Joanna, I want to buy a quantity of a US stock in a couple of clicks so that I can act on news without waiting for a call back. | AC1. Given I am signed in with an active, trading-enabled account, when I choose a supported US stock, enter a whole-number quantity greater than 0 and confirm Buy, then the order is stored with status Submitted and I see its order reference within 2 seconds. AC2. Given the quantity is empty, zero, negative or not a whole number, when I try to submit, then submission is blocked with an inline message. AC3. Given the stock is not on the supported list, when an order for it is submitted (UI or API), then it is rejected with the reason 'Only supported US stocks can be traded'. AC4. Given my account is closed, blocked or has no trading permission, when I submit an order, then it is rejected with a reason I can understand. AC5. Given I am a first-time user, then order entry is a single screen with at most one confirmation step. | Ready now | Order contract (C1); supported stock list (C5) | S10, S12, S13 | Q7 (non-blocking) | Validation rules plug in separately (S10–S13), so this story no longer waits on them.
S09 | Order Management | LMKT-21 | In Progress | LMKT-20, LMKT-32 | BR-04, §9.5 | Must | 3 | Place a market sell order | As Joanna, I want to sell some or all of a stock I hold so that I can take profits or cut losses myself. | AC1. Given I am signed in with trading permission, when I open the sell screen, then I can choose only stocks I hold and I see the quantity held for each. AC2. Given I enter a whole-number quantity greater than 0 and confirm Sell, then the order is stored with status Submitted and I see its order reference within 2 seconds. AC3. Given the quantity is empty, zero, negative or not a whole number, when I try to submit, then submission is blocked with an inline message. AC4. Given the stock is not on the supported list, or my account is closed, blocked or without trading permission, when an order is submitted, then it is rejected with a reason. | Ready now | Order contract (C1); seed holdings (C3) | S11, S12, S13 | Q7 (non-blocking)
S10 | Order Management | LMKT-22 | Done |  | BR-05 | Must | 3 | Reject buy orders the client can't afford | As David, head of trading operations, I want every buy order checked against the client's available cash before it is accepted so that no client can buy more than they can pay for. | AC1. Given available cash is at least quantity × current quote, when a submitted buy order is validated, then it passes the cash check. AC2. Given available cash is less than the estimated cost, then the order is Rejected with a reason showing required and available amounts, and no cash or holdings change. AC3. Given the client has accepted buy orders not yet filled, then the cash committed to them is excluded from available cash. AC4. Given two buy orders arrive at the same moment that together exceed available cash, then only the orders that fit are accepted. | Done | Order contract (C1); seed cash (C3) | S08 |  | AC3–4 are likely gaps in the delivered code – raise a follow-up if unmet.
S11 | Order Management | LMKT-23 | Done |  | BR-05 | Must | 2 | Reject sell orders for more than the client holds | As David, I want every sell order checked against the client's holding before it is accepted so that clients cannot sell shares they don't own. | AC1. Given the client holds at least the quantity being sold, when a submitted sell order is validated, then it passes the holdings check. AC2. Given the client holds less than the quantity, then the order is Rejected with a reason showing the quantity held. AC3. Given the client has accepted sell orders not yet filled, then that quantity is excluded from what can be sold. | Done | Order contract (C1); seed holdings (C3) | S09 |  | AC3 may be a gap – raise a follow-up if unmet.
S12 | Order Management | LMKT-24 | Done |  | BR-05 | Must | 3 | Reject orders when a stock isn't tradable right now | As David, I want orders for suspended stocks, or orders placed while the US market is closed, rejected before acceptance so that we never accept a trade we can't execute. | AC1. Given the stock is marked tradable and the market is open (hours configurable, default 9:30–16:00 ET excluding US market holidays), when a submitted order is validated, then it passes the tradability check. AC2. Given the stock is suspended or halted, or the market is closed, then the order is Rejected with the reason 'This stock can't be traded right now'. AC3. Given Trading Operations changes a stock's tradable status or the market calendar, then the change applies to the next order without a redeploy. | Done | Seed data: one suspended stock (C3); config (C5) | S08, S09 | Q5, Q6 (non-blocking) | Re-verify market-hours handling against delivered code.
S13 | Order Management | LMKT-25 | To Do |  | BR-05 | Must | 3 | Block orders that are restricted for the client's location | As Risk & Compliance, I want orders blocked when the client's location isn't allowed to trade that stock so that the firm doesn't breach market rules. | AC1. Given the client's registered country is on the restriction list for the stock, when a submitted order is validated, then it is Rejected with a reason that the stock isn't available in their location. AC2. Given the client's country is not restricted, then the order passes the location check. AC3. Given Risk & Compliance updates the restriction list, then the new rules apply to the next order without a redeploy. | Ready now | Restriction list as data, seeded with a sample rule (C3, C5) | S08, S09 | Q5 (blocks go-live only) | Build now against sample rules; load the official list when it arrives.
S14 | Order Management | LMKT-26 | Done |  | BR-06, §9.1 | Must | 3 | Commit accepted orders before execution | As David, I want an order that passes validation saved as a firm commitment before execution starts so that the client's instruction is never lost. | AC1. Given an order passes all validation, when it is accepted, then it is durably stored with status Accepted before any execution attempt begins. AC2. Given the platform restarts while accepted orders are waiting, then after restart those orders are still present with status Accepted. AC3. Given an order is accepted, then an 'accepted' audit event is emitted (C2). | Done | Order contract (C1); audit event format (C2) | S15 |  | Execution retry moved to S16 so this story stands alone. Re-verify AC2–3.
S15 | Order Management | LMKT-27 | To Do |  | BR-08 | Must | 5 | Fill an accepted order at the current market price | As Joanna, I want my order filled at the live market price when it executes so that my fill reflects the market at that moment. | AC1. Given an Accepted order and a quote no older than the staleness limit (configurable, default 5 seconds), when the order executes, then it is filled at that quote and its status becomes Filled. AC2. Given the only quote is stale or there is none, when the order executes, then it is Rejected with the reason 'Price unavailable' and is not filled at the stale price. AC3. Given the order is filled, then the quote used (price, source, quote time) and the execution time are stored with the fill, and an 'OrderFilled' event is published (C6). AC4. Given the order is filled or rejected at execution, then the matching audit event is emitted (C2). | Ready now | Seeded Accepted orders (C3); simulated quote feed (C4) | S14, S16, S17, S18 | Q4 (non-blocking) | Does not wait on S14: works from any Accepted order in the seed data.
S16 | Order Management | NEW |  |  | BR-06, §9.1 | Must | 3 | Retry execution after a failure without double-filling | As David, I want orders that fail or stall during execution to be retried safely so that a client's accepted order is neither lost nor filled twice. | AC1. Given execution fails or the execution service is unavailable, then the order shows as Pending to the client and is not rejected. AC2. Given the execution service recovers, then Pending orders are retried automatically. AC3. Given an order's execution is retried, then it is filled at most once. AC4. Given the platform restarts with Pending orders, then they are retried after restart. | Ready now | Execution interface (C6) with a stub executor that can be made to fail | S15 |  | Split out of the old 'Never lose an accepted order' story. Build the retry wrapper against the stub; swap in the real executor when S15 lands.
S17 | Order Management | LMKT-29 | To Do |  | BR-09, §9.1 | Must | 5 | Settle a buy fill | As David, I want a buy fill to update the client's cash, holding and trade record as one unit so that an account can never be left half-updated. | AC1. Given an OrderFilled event for a buy of quantity Q at price P, then cash decreases by Q × P, the holding increases by Q (created if new) and the trade record is written, all in one atomic commit. AC2. Given a failure at any point during settlement, then none of the three changes and the fill stays unsettled and recoverable. AC3. Given the same fill event is received twice, then it is applied once. AC4. Given settlement would make cash negative, then it is not applied and Trading Operations is alerted. AC5. Given settlement completes, then a 'settled' audit event is emitted with the cash and holding changes (C2). | Ready now | OrderFilled event contract (C6); seeded fills and balances (C3) | S15, S18 |  | Split from the old 8-point settlement story. S17 and S18 can be worked in parallel; whichever lands first sets up the shared settlement transaction.
S18 | Order Management | LMKT-30 | To Do |  | BR-09, §9.1 | Must | 3 | Settle a sell fill | As David, I want a sell fill to update the client's cash, holding and trade record as one unit so that an account can never be left half-updated. | AC1. Given an OrderFilled event for a sell of quantity Q at price P, then cash increases by Q × P, the holding decreases by Q (removed at zero) and the trade record is written, all in one atomic commit. AC2. Given a failure at any point during settlement, then none of the three changes and the fill stays unsettled and recoverable. AC3. Given the same fill event is received twice, then it is applied once. AC4. Given settlement would make a holding negative, then it is not applied and Trading Operations is alerted. AC5. Given settlement completes, then a 'settled' audit event is emitted (C2). | Ready now | OrderFilled event contract (C6); seeded fills and holdings (C3) | S15, S17
S19 | Order Management | LMKT-28 | To Do |  | BR-07, §9.2 | Should | 3 | See my order status change live | As Joanna, I want to see my order move through its statuses without refreshing so that I never wonder whether my trade went through. | AC1. Given I have an open order, when its status changes (Submitted → Accepted → Pending → Filled or Rejected), then the new status appears on screen within 2 seconds without a manual refresh. AC2. Given my order is Rejected, then the reason is shown in plain language. AC3. Given my order is Filled, then the fill price and quantity are shown. AC4. Given my connection drops, then I see a 'Reconnecting…' indicator and the latest statuses once I reconnect. | Ready now | OrderStatusChanged event contract (C6); status changes triggered from seed data/test tool | S08, S09, S15
S20 | Order Management | NEW |  |  | BR-10, §9.2 | Should | 2 | See my holdings and cash update live after a fill | As Joanna, I want my holdings and cash to change on screen as soon as an order fills so that I can trust I'm looking at my real position. | AC1. Given I am viewing my portfolio, when one of my orders is settled, then my holdings and cash on screen update within 2 seconds without a refresh. AC2. Given my connection drops, then the latest holdings and cash are shown once I reconnect. | Pull after S19, S21, S22 | Live channel from S19; portfolio views from S21/S22 | S17, S18 |  | One of only three stories with a real dependency: it joins two finished features, so it is kept small.
S21 | Portfolio Management | LMKT-33 | To Do | LMKT-37 | BR-10 | Must | 3 | View my holdings | As Joanna, I want to see what I own so that I can trust that what's on screen is my real position. | AC1. Given I am signed in, when I open my portfolio, then I see each stock I hold with its quantity, as currently recorded. AC2. Given I hold nothing, then I see a friendly empty state with a link to place an order. AC3. Given the platform has restarted, then my holdings are exactly as they were before. | Ready now | Seed holdings (C3); portfolio API contract (C6) | S20 |  | Live updating moved to S20 so this reads straight from seed data.
S22 | Portfolio Management | LMKT-34 | To Do | LMKT-38 | BR-10 | Must | 2 | View my cash balance | As Joanna, I want to see my cash balance so that I know how much I can invest. | AC1. Given I am signed in, when I open my portfolio, then I see my cash balance in US dollars to 2 decimal places, as currently recorded. AC2. Given I have accepted buy orders not yet filled, then the cash available to trade is shown alongside the total balance. AC3. Given the platform has restarted, then the balance is exactly as it was before. | Ready now | Seed cash and Accepted orders (C3); portfolio API contract (C6) | S20
S23 | Portfolio Management | LMKT-35 | To Do | LMKT-39 | BR-11 | Must | 3 | View my order history | As Joanna, I want a chronological list of my orders and fills so that I can review what I've traded. | AC1. Given I am signed in, when I open order history, then I see my orders newest first with date/time, stock, side, quantity, status and fill price. AC2. Given an order was rejected, then its rejection reason is shown. AC3. Given I have no orders, then I see an empty state. AC4. Given I have more than 50 orders, then the list is paginated. | Ready now | Seed orders in every status (C3) | S24 | Q8 (non-blocking)
S24 | Portfolio Management | LMKT-36 | To Do |  | BR-11 | Must | 2 | Filter my order history by day, month or year | As Joanna, I want to filter my order history by date so that I can find a particular trade quickly. | AC1. Given I choose a day, month or year, then only orders placed in that period (in my local time zone) are shown. AC2. Given no orders match, then I see 'No orders in this period'. AC3. Given I clear the filter, then the full history returns. | Ready now | Order history API (C6); seed orders spanning several days, months and years (C3) | S23 |  | Can be built as the API filter plus UI control in parallel with S23; they meet at the shared contract.
S25 | Market Data | LMKT-40 | Done | LMKT-42 | BR-12 | Must | 3 | Price orders from live US stock quotes | As Joanna, I want US stocks priced from a live quote feed so that I trade at real market prices. | AC1. Given a supported US stock ticker, when the platform requests a quote, then it receives a price and the time of that quote. AC2. Given an unknown or unsupported ticker, then a 'Stock not found' error is returned and no price. AC3. Given the quote source is changed by configuration (simulated feed ↔ live provider), then no code change is needed. | Done | — | S15, S26, S27 | Q7 | Re-verify AC3 against delivered code.
S26 | Market Data | LMKT-41 | To Do |  | BR-08, BR-12, §9.1 | Must | 2 | Protect clients when the quote feed fails | As David, I want the platform to detect a failed quote feed so that no client is shown or filled at a wrong or stale price. | AC1. Given the quote feed is unavailable or times out, then quote requests return 'Price unavailable' rather than the last known price. AC2. Given the feed is unavailable, when a client is on the order screen, then they see 'Prices are temporarily unavailable'. AC3. Given the feed recovers, then pricing resumes automatically without a restart. AC4. Given an outage, then its start and end are recorded for Trading Operations. | Ready now | Simulated feed with an on/off failure switch (C4) | S15, S27
S27 | Market Data | LMKT-45 | To Do | LMKT-46 | BR-13 | Should | 3 | See an indicative price before I submit | As Joanna, I want to see roughly what my order will cost before I submit it so that I'm not surprised by the fill. | AC1. Given I select a stock on the order screen, then its current indicative price and the time of that price are shown. AC2. Given I enter a quantity, then an estimated total (quantity × indicative price) is shown. AC3. Given an indicative price is shown, then it is labelled 'Indicative – your fill price may differ'. AC4. Given the order screen stays open, then the price refreshes at least every 5 seconds. AC5. Given no price is available, then 'Price unavailable' is shown instead of a number. | Ready now | Quote API (S25 is Done); simulated feed (C4) | S08, S09
S28 | Audit & Compliance | LMKT-47 | To Do |  | BR-14, §9.1 | Must | 3 | Record order submission and validation events | As Risk & Compliance, I want every order submission and every validation result permanently recorded so that the firm can show why each order was accepted or rejected. | AC1. Given an order is submitted, then a 'submitted' audit event is recorded with client ID, order ID and server UTC time. AC2. Given each validation check runs, then an event is recorded with the rule checked and its result. AC3. Given the platform restarts or a deployment fails, then no event is lost or duplicated. | Ready now | Audit event format (C2); existing submission and validation code | S08–S13 |  | The other lifecycle events (accepted, filled, settled) are emitted by S14, S15, S17 and S18 themselves, so audit no longer waits on execution being built.
S29 | Audit & Compliance | LMKT-49 | To Do |  | BR-14, §9.4 | Must | 3 | Prevent any change or deletion of audit records | As Risk & Compliance, I want trade records to be impossible to edit or delete so that they stand up to a regulator's inspection at any time. | AC1. Given an audit record exists, then no application feature or API allows it to be updated or deleted. AC2. Given the application's database account, then it has no permission to update or delete audit records; any attempt fails and is itself recorded. | Ready now | Seed audit events (C3) | —
S30 | Audit & Compliance | NEW |  |  | BR-14, §9.4 | Must | 3 | Retain and archive audit records for 7 years | As Risk & Compliance, I want old audit records archived rather than deleted and kept for at least 7 years so that we meet our legal retention duty. | AC1. Given a record is older than the online retention window (configurable), then it is moved to archive rather than deleted. AC2. Given a record is in archive, then it is kept for at least 7 years from creation. AC3. Given Risk & Compliance requests an archived record, then it can be retrieved. | Ready now | Seed audit events with back-dated timestamps (C3); config (C5) | — | Q9 (non-blocking) | Split out of the old immutability story.
S31 | Audit & Compliance | LMKT-50 | To Do |  | BR-15, §9.3 | Must | 3 | Find a trade by order ID or by client and date | As David, I want to find any trade quickly so that I can start answering a client dispute straight away. | AC1. Given I am signed in with the Trading Operations role, when I search by order ID, then I see that trade. AC2. Given I search by client and date range, then I see that client's trades in the range. AC3. Given a client (not staff) tries to use this search, then access is denied. | Ready now | Seed staff users and roles (C3, C7); seed trades (C3) | S32
S32 | Audit & Compliance | NEW |  |  | BR-15, §9.3 | Must | 3 | View a trade's full event timeline | As David, I want to see step by step what happened to a trade and when so that I can answer an audit or dispute without asking engineering to dig through logs. | AC1. Given I open a trade by its order ID (Trading Operations role), then I see a chronological timeline of every audit event with its time and details, including the quote used and the cash and holding changes. AC2. Given the timeline is shown, then it is built only from the audit trail, not from application logs. AC3. Given a client (not staff) tries to open this view, then access is denied. | Ready now | Seed audit events for several complete trades (C3); role model (C7) | S31 |  | Opens directly by order ID, so it doesn't wait on the search in S31.
S33 | Reporting | LMKT-53 | To Do | LMKT-51 | BR-16 | Must | 3 | Report trade counts and values by period | As Priya, a commercial analyst, I want trading activity by day, week, month and year so that I can report volumes to the executive committee. | AC1. Given I choose a period type (daily, weekly, monthly or yearly) and a date range, then I see, for each period, the trade count, buy count, sell count and total traded value. AC2. Given a typical report (up to one year of data), then it is generated within 10 seconds. AC3. Given I am not signed in with an internal reporting role, then I cannot access the report. | Ready now | Seed settled trades across a year (C3); reporting data source per architecture (C6); role model (C7) | S36
S34 | Reporting | LMKT-52 | To Do |  | BR-16 | Must | 3 | Report trading activity by stock | As Priya, I want trading activity broken down by stock so that I can see which stocks drive volume. | AC1. Given I choose a date range, then I see, per stock, the trade count, quantity traded and total traded value, sortable by any column. AC2. Given a typical report, then it is generated within 10 seconds. AC3. Given I am not signed in with an internal reporting role, then I cannot access the report. | Ready now | Seed settled trades (C3); role model (C7) | S36
S35 | Reporting | NEW |  |  | BR-16 | Must | 3 | Report trading activity by client segment | As Priya, I want trading activity broken down by client segment so that I can see how different kinds of clients behave. | AC1. Given I choose a date range, then I see, per client segment, the number of active clients, trade count and total traded value. AC2. Given a typical report, then it is generated within 10 seconds. AC3. Given the report is shown, then no individual client is identifiable from it. | Ready now | Segment held as a client attribute, seeded with sample segments (C3) | S36 | Q10 (non-blocking) | Build now; plug in the real segment definitions when the PO provides them.
S36 | Reporting | NEW |  |  | BR-16, §9.2 | Must | 3 | Keep reporting from slowing down live trading | As Joanna, I want my orders confirmed just as quickly while the business runs reports so that my trading is never held up by internal analysis. | AC1. Given reports are running during trading hours, then client order confirmation times stay within their normal target. AC2. Given the above, then it is proven by an automated load test that runs reports and orders together. | Pull after S33 | One working report (S33) plus seed load (C3) | S33, S34, S35 |  | Performance split out of the report stories (defer-performance pattern) so the reports can be built first.
S37 | Reporting | NEW |  |  | BR-16 | Must | 3 | Generate long-running reports overnight | As Priya, I want heavy reports produced overnight so that they're ready in the morning without slowing anything down during the day. | AC1. Given a report is marked as an overnight report, then it runs automatically outside trading hours. AC2. Given the overnight run succeeds, then the report is available by 07:00 (configurable). AC3. Given the overnight run fails, then I am notified and can see the reason. | Ready now | A stub report job; config (C5) | S33, S34, S35 |  | Build the scheduler against a stub job; point it at real reports as they land.
S38 | Reporting | LMKT-54 | To Do |  | BR-17 | Should | 2 | Insight: trading volume compared with the previous period | As Priya, I want to see today's and this week's trading volume against the previous period as soon as I open reporting so that I spot changes in activity at a glance. | AC1. Given I open the reporting area, then I see today's and this week's traded volume, each with the change from the previous period. AC2. Given the insight is shown, then it shows when it was last refreshed, and it refreshes at least daily. AC3. Given I am not an internal user, then I cannot see it. | Ready now | Seed settled trades (C3); role model (C7) | — |  | The old 'insight dashboard' split into one story per insight. Replaces LMKT-54's client metrics, which weren't BR-17 insights.
S39 | Reporting | NEW |  |  | BR-17 | Should | 2 | Insight: most active stocks | As Priya, I want to see the 5 most actively traded stocks so that I know where client interest is concentrated. | AC1. Given I open the reporting area, then I see the 5 most traded stocks for this week by traded value. AC2. Given the insight is shown, then it shows when it was last refreshed, and it refreshes at least daily. AC3. Given I am not an internal user, then I cannot see it. | Ready now | Seed settled trades (C3); role model (C7) | —
S40 | Reporting | NEW |  |  | BR-17 | Should | 2 | Insight: active-client trend | As Priya, I want to see how many clients traded each day over the last 30 days so that I can spot growth or decline in client activity. | AC1. Given I open the reporting area, then I see the number of clients who traded each day over the last 30 days. AC2. Given the insight is shown, then it shows when it was last refreshed, and it refreshes at least daily. AC3. Given I am not an internal user, then I cannot see it. | Ready now | Seed settled trades across 30+ days (C3); role model (C7) | —
S41 | Enhancements | NEW |  |  | BR-18 | Should | 3 | Keep a personal watchlist (candidate differentiator) | As Joanna, I want to keep a watchlist of stocks I'm interested in so that I can check their prices in the evening without searching each time. | AC1. Given I am signed in, when I add a stock to my watchlist, then it appears in the list with its current indicative price. AC2. Given I remove a stock, then it disappears from the list. AC3. Given I sign out and back in, then my watchlist is unchanged. | Ready – awaiting PO choice | Quote API (S25 is Done) | — | Q11 (decides whether this is built) | Candidate only. BR-18 requires the team to pick ONE capability and justify it.

## Shared Contracts
ID | Contract | What it defines | Why it removes waiting | Used by
C1 | Order model and status lifecycle | Order fields; statuses Submitted → Accepted → Pending → Filled / Rejected; rejection reason codes. | Every order story codes against the same shape, so validation, execution and history can be built in parallel. | S08–S19, S23
C2 | Audit event format | Event types (submitted, validated, accepted, filled, rejected, settled); fields: client ID, order ID, UTC time, details. Rule: written in the same transaction as the change. | Each lifecycle story emits its own events, so audit doesn't wait on execution. | S14, S15, S17, S18, S28–S32
C3 | Seed / test data set | Clients (active, closed, expired, locked, no trading permission); staff users with Trading Ops, Analyst and Compliance roles; supported US stocks incl. one suspended; holdings and cash; orders in every status across several days, months and years; Accepted orders awaiting execution; fills; settled trades over 12 months; client segments; audit events for several complete trades. | Read-side stories (portfolio, audit, reporting) can be built and demoed without the write-side being finished. | Almost all
C4 | Simulated quote feed | Controllable prices per stock; switch to make quotes stale or the feed unavailable on demand. | Pricing, failure handling and indicative price can be tested without a live provider. | S15, S26, S27, S41
C5 | Configuration settings | Inactivity timeout; lockout attempts and duration; staleness limit; market hours and holidays; supported stock list; location restriction list; audit online retention window; overnight report time. | Open questions become config values instead of blockers. | S03, S04, S08, S12, S13, S15, S30, S37
C6 | API and event contracts | REST endpoints and payloads for orders, portfolio, quotes, audit and reports; internal events OrderStatusChanged and OrderFilled; execution interface; reporting data source. | Front-end and back-end halves of a story, or neighbouring stories, meet at an agreed contract. | All
C7 | Role model | Client vs staff; staff roles carried in the session; which roles see which internal views. | Internal views (audit, reports, insights) can enforce access without waiting on a staff admin feature. | S31–S40

## Jira Change Plan
Jira Key | Type | Current Summary | Current Status | Assignee | Proposed Action | New Story
LMKT-2 | Epic | Authentication & Security | To Do |  | Keep epic. No change.
LMKT-3 | Epic | Order Management | To Do |  | Keep epic. No change.
LMKT-4 | Epic | Portfolio Management | To Do |  | Keep epic. No change.
LMKT-5 | Epic | Market Data | To Do |  | Keep epic. No change.
LMKT-6 | Epic | Audit & Compliance | To Do |  | Keep epic. No change.
LMKT-7 | Epic | Reporting | To Do |  | Keep epic. No change.
LMKT-8 | Epic | Enhancements | To Do |  | Keep epic. No change.
LMKT-9 | Story | Registration form | Done |  | Merged into S01 (LMKT-11). Link to LMKT-11; leave as Done (history). | S01
LMKT-10 | Story | Validation feedback | Done |  | Merged into S01 (LMKT-11). Link to LMKT-11; leave as Done (history). | S01
LMKT-11 | Story | Create account | Done |  | Rewrite summary + description as S01 "Register for an account". Keep status, assignee, sprint. | S01
LMKT-12 | Story | Reject duplicate emails | Done |  | Merged into S01 (LMKT-11). Link to LMKT-11; leave as Done (history). | S01
LMKT-13 | Story | Login page | Done |  | Merged into S02 (LMKT-14). Link to LMKT-14; leave as Done (history). | S02
LMKT-14 | Story | Authenticate credentials | Done |  | Rewrite summary + description as S02 "Sign in securely". Keep status, assignee, sprint. | S02
LMKT-15 | Story | Create JWT session | Done |  | Merged into S02 (LMKT-14). Link to LMKT-14; leave as Done (history). | S02
LMKT-16 | Story | View only own data | Done | Aditya Bapanapalli | Rewrite summary + description as S07 "See and act on only my own account". Keep status, assignee, sprint. | S07
LMKT-17 | Story | Session timeout | Done | Amara | Rewrite summary + description as S04 "Sign me out automatically after inactivity". Keep status, assignee, sprint. | S04
LMKT-18 | Story | Account lockout | To Do |  | Rewrite summary + description as S03 "Lock my account after repeated failed sign-ins". Keep status, assignee, sprint. | S03
LMKT-19 | Story | Buy order form | Done | Johan Dabare | Merged into S08 (LMKT-55). Link to LMKT-55; leave as Done (history). | S08
LMKT-20 | Story | Sell order form | Done | Johan Dabare | Merged into S09 (LMKT-21). Link to LMKT-21; leave as Done (history). | S09
LMKT-21 | Story | Submit sell order microservce | In Progress | siddiwal48 | Rewrite summary + description as S09 "Place a market sell order". Keep status, assignee, sprint. | S09
LMKT-22 | Story | Validate cash | Done | Joseph Farghal | Rewrite summary + description as S10 "Reject buy orders the client can't afford". Keep status, assignee, sprint. | S10
LMKT-23 | Story | Validate holdings | Done | Amara | Rewrite summary + description as S11 "Reject sell orders for more than the client holds". Keep status, assignee, sprint. | S11
LMKT-24 | Story | Tradability check | Done | siddiwal48 | Rewrite summary + description as S12 "Reject orders when a stock isn't tradable right now". Keep status, assignee, sprint. | S12
LMKT-25 | Story | Geographic restrictions | To Do |  | Rewrite summary + description as S13 "Block orders that are restricted for the client's location". Keep status, assignee, sprint. | S13
LMKT-26 | Story | Persist orders | Done | Aditya Bapanapalli | Rewrite summary + description as S14 "Commit accepted orders before execution". Keep status, assignee, sprint. | S14
LMKT-27 | Story | Execute trade | To Do |  | Rewrite summary + description as S15 "Fill an accepted order at the current market price". Keep status, assignee, sprint. | S15
LMKT-28 | Story | View order status | To Do |  | Rewrite summary + description as S19 "See my order status change live". Keep status, assignee, sprint. | S19
LMKT-29 | Story | Update holdings | To Do |  | Rewrite summary + description as S17 "Settle a buy fill". Keep status, assignee, sprint. | S17
LMKT-30 | Story | Update cash balance | To Do |  | Rewrite summary + description as S18 "Settle a sell fill". Keep status, assignee, sprint. | S18
LMKT-31 | Story | Buy order integration | In Progress | Aditya Bapanapalli | Merged into S08 (LMKT-55). Link to LMKT-55; close once the assignee confirms the rewritten story covers the remaining work. | S08
LMKT-32 | Story | Sell order integration | In Progress | Aditya Bapanapalli | Merged into S09 (LMKT-21). Link to LMKT-21; close once the assignee confirms the rewritten story covers the remaining work. | S09
LMKT-33 | Story | View holdings | To Do |  | Rewrite summary + description as S21 "View my holdings". Keep status, assignee, sprint. | S21
LMKT-34 | Story | View cash balance | To Do |  | Rewrite summary + description as S22 "View my cash balance". Keep status, assignee, sprint. | S22
LMKT-35 | Story | View order history | To Do |  | Rewrite summary + description as S23 "View my order history". Keep status, assignee, sprint. | S23
LMKT-36 | Story | Filter order history | To Do |  | Rewrite summary + description as S24 "Filter my order history by day, month or year". Keep status, assignee, sprint. | S24
LMKT-37 | Story | Holdings page integration | To Do |  | Merged into S21 (LMKT-33). Link to LMKT-33; close once the assignee confirms the rewritten story covers the remaining work. | S21
LMKT-38 | Story | Cash balance integration | To Do |  | Merged into S22 (LMKT-34). Link to LMKT-34; close once the assignee confirms the rewritten story covers the remaining work. | S22
LMKT-39 | Story | Order history integration | To Do |  | Merged into S23 (LMKT-35). Link to LMKT-35; close once the assignee confirms the rewritten story covers the remaining work. | S23
LMKT-40 | Story | Retrieve quotes | Done | siddiwal48 | Rewrite summary + description as S25 "Price orders from live US stock quotes". Keep status, assignee, sprint. | S25
LMKT-41 | Story | Handle quote failures | To Do |  | Rewrite summary + description as S26 "Protect clients when the quote feed fails". Keep status, assignee, sprint. | S26
LMKT-42 | Story | Equity quotes | To Do |  | Merged into S25 (LMKT-40). Link to LMKT-40; close once the assignee confirms the rewritten story covers the remaining work. | S25
LMKT-43 | Story | FX quotes | To Do |  | Out of scope – PO decision: US stocks only. Close as Won't Do.
LMKT-44 | Story | Crypto quotes | To Do |  | Out of scope – PO decision: US stocks only. Close as Won't Do.
LMKT-45 | Story | Indicative pricing | To Do |  | Rewrite summary + description as S27 "See an indicative price before I submit". Keep status, assignee, sprint. | S27
LMKT-46 | Story | Market data integration | In Progress | Amara | Merged into S27 (LMKT-45). Link to LMKT-45; close once the assignee confirms the rewritten story covers the remaining work. | S27
LMKT-47 | Story | Record order events | To Do |  | Rewrite summary + description as S28 "Record order submission and validation events". Keep status, assignee, sprint. | S28
LMKT-48 | Story | Record settlement events | To Do |  | Merged: settlement events are now emitted by S17/S18 (LMKT-29/LMKT-30). Link to both; close.
LMKT-49 | Story | Immutable audit records | To Do |  | Rewrite summary + description as S29 "Prevent any change or deletion of audit records". Keep status, assignee, sprint. | S29
LMKT-50 | Story | Trade lifecycle view | To Do |  | Rewrite summary + description as S31 "Find a trade by order ID or by client and date". Keep status, assignee, sprint. | S31
LMKT-51 | Story | Trading activity report | To Do |  | Merged into S33 (LMKT-53). Link to LMKT-53; close once the assignee confirms the rewritten story covers the remaining work. | S33
LMKT-52 | Story | Instrument analytics | To Do |  | Rewrite summary + description as S34 "Report trading activity by stock". Keep status, assignee, sprint. | S34
LMKT-53 | Story | Period analytics | To Do |  | Rewrite summary + description as S33 "Report trade counts and values by period". Keep status, assignee, sprint. | S33
LMKT-54 | Story | Insight dashboard | To Do |  | Rewrite summary + description as S38 "Insight: trading volume compared with the previous period". Keep status, assignee, sprint. | S38
LMKT-55 | Story | Submit buy order microservice | In Progress | siddiwal48 | Rewrite summary + description as S08 "Place a market buy order". Keep status, assignee, sprint. | S08
LMKT-56 | Story | Registration integration | Done |  | Merged into S01 (LMKT-11). Link to LMKT-11; leave as Done (history). | S01
LMKT-57 | Story | Sign on integration | Done |  | Merged into S02 (LMKT-14). Link to LMKT-14; leave as Done (history). | S02
LMKT-58 | Story | Finalize Mockup for Login | Done | Johan Dabare | Change issue type to Task (design work). No other change.
LMKT-59 | Story | Finalize Mockup for Registration | Done | Johan Dabare | Change issue type to Task (design work). No other change.
LMKT-60 | Story | Finalize Mockup for Dashboard | Done | William Nguyen | Change issue type to Task (design work). No other change.
LMKT-61 | Story | Finalize Mockup for Buy/Sell | Done | William Nguyen | Change issue type to Task (design work). No other change.
LMKT-62 | Story | REDO STORIES | In Progress | Joseph Farghal | Change issue type to Task. This workbook is its output.
LMKT-63 | Story | Microservice Architecture | In Progress | William Nguyen | Change issue type to Task. Link to the new "Shared contracts & seed data" task (its API/event contracts are C6).
(new) | Task | Shared contracts & seed data (C1–C7) |  |  | Create FIRST, before sprint planning. Small, time-boxed; most parts already exist (LMJ-32 schema, LMKT-40 quotes, LMKT-26 order persistence).
(new) | Story | Sign out |  |  | Create as S05 under the Authentication & Security epic. | S05
(new) | Story | Cut off access for closed or expired accounts |  |  | Create as S06 under the Authentication & Security epic. | S06
(new) | Story | Retry execution after a failure without double-filling |  |  | Create as S16 under the Order Management epic. | S16
(new) | Story | See my holdings and cash update live after a fill |  |  | Create as S20 under the Order Management epic. | S20
(new) | Story | Retain and archive audit records for 7 years |  |  | Create as S30 under the Audit & Compliance epic. | S30
(new) | Story | View a trade's full event timeline |  |  | Create as S32 under the Audit & Compliance epic. | S32
(new) | Story | Report trading activity by client segment |  |  | Create as S35 under the Reporting epic. | S35
(new) | Story | Keep reporting from slowing down live trading |  |  | Create as S36 under the Reporting epic. | S36
(new) | Story | Generate long-running reports overnight |  |  | Create as S37 under the Reporting epic. | S37
(new) | Story | Insight: most active stocks |  |  | Create as S39 under the Reporting epic. | S39
(new) | Story | Insight: active-client trend |  |  | Create as S40 under the Reporting epic. | S40
(new) | Story | Keep a personal watchlist (candidate differentiator) |  |  | Create as S41 under the Enhancements epic. | S41
LMJ-* | — | LeMarketJames OLD project |  |  | No change.

## Open Questions
# | Question | Affects | Blocks development?
Q1 | Registration fields: BR-01 lists Name, Address, Email, Phone. LMJ-1 also had SSN, DOB, initial deposit, investing experience. Which are required? | S01 | No – BRS fields are built; extra fields would be a new story.
Q2 | Inactivity timeout: BRS says 1 minute, LMJ-4 said 10. Confirm. | S04 | No – configurable, default 1 minute.
Q3 | Lockout: unlock automatically after a period, or by staff? | S03 | No – auto-unlock after 15 minutes by default; staff unlock would be a new story.
Q4 | Stale quote: what age is stale, and should a stale order be rejected or held as Pending? | S15, S26 | No – configurable 5 s default; rejects by default.
Q5 | Official trading rules and location restriction list. | S12, S13 | No for development (rules are data, seeded with samples). Yes for go-live.
Q6 | Trading session: regular hours only, or pre-market and after-hours too? | S12 | No – market hours are configurable.
Q7 | Which US securities count as "stocks": NYSE/Nasdaq common shares only, or ETFs, ADRs and OTC too? | S08, S09, S25 | No – the supported list is data.
Q8 | Order history: newest-first (built) or oldest-first? | S23 | No – trivial to change.
Q9 | Audit archive: online window before archiving, and archive retrieval time? | S30 | No – configurable.
Q10 | How are client segments defined? | S35 | No – segment is a client attribute seeded with samples.
Q11 | Which ONE differentiator for BR-18, and why? | S41 | Yes – decides whether S41 is built at all.
Q12 | Responsiveness targets: 2 s for live updates, 10 s for reports. Confirm. | S08, S09, S19, S20, S33–S35 | No – numbers only.

## Definition of Done
# | Applies to every story
1 | Code reviewed and merged to the main branch.
2 | Automated tests cover every acceptance criterion; all pass in the Jenkins pipeline.
3 | Docker image builds and deploys to the shared test environment.
4 | Each acceptance criterion demonstrated to the Product Owner.
5 | No client data exposed across accounts (S07 checks run in CI for every new endpoint).
6 | Any new state change writes its audit event in the same transaction (C2).
7 | Built only against the shared contracts (C1–C7); any change to a contract is agreed with the team first.
8 | If a story in "Integrates With" is already Done, an end-to-end test covers the join.
9 | Any new setting is added to the configuration list (C5) with its default.

## Scope Decisions
Date | Source | Decision | Deviation from BRS | Backlog Impact
22 Sep 2026 | Product Owner meeting | Platform trades US markets only, and stocks only. | Narrows BR-12 (BRS listed UK/US/Indian equities, FX and crypto). | Removed Indian/UK equities, FX (LMKT-43) and crypto (LMKT-44). Orders, quotes and tradability reference US stocks and US market hours. Cash is USD only.